## PROJECT PLAN
PROJECT NAME:MEDIC AID 003 Timeline - 24/08/2022 - 30/11/2022
S/N | Action item/Deliverables | Owner | Start Date | End Date | Status
Week1 | Conduct Gap Analysis | BAs | 2022-08-24 | 2022-08-30 | Done
Week1 | Create a Project Scope Document | BAs | 2022-08-24 | 2022-08-30 | Done
Week2 | Prepare Requirement gathering workshop agenda | BAs | 2022-08-31 | 2022-09-06 | Done
Week2 | Hold Requirement gathering workshop | BAs | 2022-08-31 | 2022-09-06 | Done
Week2 | Identity and document high and low level requirement | BAs | 2022-08-31 | 2022-09-06 | Done
Week2 | Start writing user stories and acceptance criteria | BAs | 2022-08-31 | 2022-09-06 | Done
Week2 | Ensure to prioritize requirements (MOSCOW) | BAs | 2022-08-31 | 2022-09-06 | Done
Week3 | Draft user stories and acceptance criteria document | BAs | 2022-09-07 | 2022-09-13 | Done
Week3 | Get Familiar with Trello and Move cards | BAs | 2022-09-07 | 2022-09-13 | Done
Week4 | Update Trello Board with Sign off Documents | BAs | 2022-09-14 | 2022-09-20 | Done
Week4 | Submit BA updated work plan | BAs | 2022-09-14 | 2022-09-20 | In Progress
Week4 | Conduct SWOT analysis | BAs | 2022-09-14 | 2022-09-20 | In Progress
Week5 | Create process Maps | BAs | 2022-09-21 | 2022-09-27 | Not started
Week5 | Submit BA updated work plan | BAs | 2022-09-21 | 2022-09-27 | Not started
Week6 | Create Wireframes | BAs | 2022-09-28 | 2022-10-04 | Not started
Week6 | Submit BA updated work plan | BAs | 2022-09-28 | 2022-10-04 | Not started
Week6 | Revise the Agile scrum guide | BAs | 2022-09-28 | 2022-10-04 | Not started
Week7 | Create a Business Model Canvas | BAs | 2022-10-05 | 2022-10-11 | Not started
Week7 | Ensure Developer and Tester are well aligned | BAs | 2022-10-05 | 2022-10-11 | Not started
Week7 | Work with Tester to create Test Plan | BAs | 2022-10-05 | 2022-10-11 | Not started
Week7 | Ensures Tester hands in UAT Document | BAs | 2022-10-05 | 2022-10-11 | Not started
Week8 | Work with Developer to validate requirements | BAs | 2022-10-12 | 2022-10-18 | Not started
Week8 | Aligh all documents with the developer | BAs | 2022-10-12 | 2022-10-18 | Not started
Week8 | Join the sprint planning meeting | BAs | 2022-10-12 | 2022-10-18 | Not started
Week8 | Support the development team | BAs | 2022-10-12 | 2022-10-18 | Not started
Week8 | Update the Trello Board | BAs | 2022-10-12 | 2022-10-18 | Not started
Week8 | Send in Assessment for Week 8 | BAs | 2022-10-12 | 2022-10-18 | Not started
Week9 | Ensure UAT is conducted after the sprint 1 Demo | BAs | 2022-10-19 | 2022-10-25 | Not started
Week9 | Send in Updated BA work Plan and Assesssment for week9 | BAs | 2022-10-19 | 2022-10-25 | Not started
Week9 | Prepare a team exercise on BA related Topic | BAs | 2022-10-19 | 2022-10-25 | Not started
Week10 | Support the development team | BAs | 2022-10-26 | 2022-11-01 | Not started
Week10 | Update the Trello Board | BAs | 2022-10-26 | 2022-11-01 | Not started
Week10 | Send in Assessment for Week 10 | BAs | 2022-10-26 | 2022-11-01 | Not started
Week11 | Ensure UAT is conducted after the sprint 2 Demo | BAs | 2022-11-02 | 2022-11-08 | Not started
Week11 | Send in assessment for week 11 | BAs | 2022-11-02 | 2022-11-08 | Not started
Week12 | Conduct Final UAT |  | 2022-11-09 | 2022-11-15 | Not started